## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description |  | Hours | Minutes
1 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-01-29 | 1 | 0 | discuss project idea and begin requirements stack | Aiden Patel | 77 | 8
2 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2025-02-02 | 1 | 0 | finalize initial requirements stack | Andrew McFerrin | 47 | 32
3 | John Newman | 2025-02-06 | 0 | 30 | wrote two requirements artifacts | John Newman | 36 | 25
4 | Landon Pyko | 2025-02-05 | 0 | 15 | wrote one artifact. forgot to write this down yesterday | Kai Achen | 32 | 45
5 | Landon Pyko | 2025-02-06 | 0 | 20 | Looked into Hugging Face and CNN. Made the GitHub repository and shared it with group | Landon Pyko | 28 | 5
6 | John Newman | 2025-02-06 | 0 | 19 | wrote 2 requirements artifacts
7 | Aiden Patel | 2025-02-07 | 0 | 20 | organized documentation on GitHub. Started initial architecture document and then remembered we have a writer on the team that'll be better at that
8 | Aiden Patel | 2025-02-07 | 0 | 30 | did a little bit of research on models and put in some starter code to get an idea of what's going on | Total Time | 221 | 55
9 | Kai Achen | 2025-02-10 | 1 | 0 | completed DubBot training programs to learn more about how alt-text works and what makes effective and successful alt-text.
10 | Andrew McFerrin | 2025-02-10 | 0 | 30 | Looked into a couple image datasets and tried to generally understand whats even going on
11 | Landon Pyko | 2025-02-12 | 0 | 45 | Did some research and think that ResNet50 will be good for image classification. Imported some starter code for it. Also made a .gitignore to ignore the venv/ directory for if people want to use a virtual environment for dependencies
12 | Landon Pyko | 2025-02-12 | 0 | 30 | Spent a lot of time downloading dependencies and setting up venv. Created an instructions folder for everyone else for setting up the environment for it. Modified starter code to take in a image that I put in an image file. Properly classifies the image in output!
13 | Aiden Patel | 2025-02-12 | 0 | 40 | put in some starter code using DETR model that can generate multiple tags per image
14 | Kai Achen | 2025-02-12 | 0 | 35 | created compile_to_csv function that compiles images, tags, and flags into a csv file format for later use
15 | Aiden Patel, Andrew McFerrin | 2025-02-12 | 0 | 15 | discussed implementation of models
16 | Aiden Patel | 2025-02-12 | 1 | 0 | got some starter code in for entity recognition for text context and then burned a bunch of time messing with venv stuff because I don't have enough storage to download the GPU stuff for pytorch on my main drive
17 | Aiden Patel | 2025-02-13 | 1 | 30 | create tag_synthesizer that takes in tags and creates a caption and also created create_caption that takes in a photo and text to combine them and make a caption. Put some examples in and there's one in place on create_caption to test it (I know it's an illogical photo and text combo but that's the point)
18 | Landon Pyko | 2025-02-13 | 0 | 15 | Started on Sprint 2 Requirements Artifacts
19 | Aiden Patel | 2025-02-13 | 0 | 45 | set up environment on my desktop. made a requirements.txt to automatically install every package we need. proibably will need to update it. now trying to get the model to run on my gpu, not working so far but will report back
20 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 5 | discuss running model on Nvidia cards
21 | Aiden Patel, Andrew McFerrin | 2025-02-13 | 0 | 12 | talk about models and realize we need another model for extracting text found on an image
22 | Landon Pyko | 2025-02-13 | 1 | 15 | Finally got it to work on my gpu.... frankly it took like twice as long as i said but i don't want to put that time in the log
23 | Aiden Patel, Landon Pyko | 2025-02-13 | 0 | 30 | talk through some code and about models being used
24 | Aiden Patel | 2025-02-14 | 0 | 45 | Rename files to be more descriptive and add caption model that helps create final output better
25 | Andrew McFerrin | 2025-02-14 | 1 | 15 | Familiarized myself with project, finished up rest of artifacts for sprint 2.
26 | Landon Pyko | 2025-02-14 | 1 | 0 | Fixed up tag generation by merging words together that started with ##. Weird thing that was happening but this fixed it. Also, did some other random stuff and made the sentence generator output grammatically correct sentences, even if it means they lose some of their meaning
27 | Aiden Patel | 2025-02-14 | 0 | 40 | Created a test script to batch test image and text combos
28 | John Newman | 2025-02-14 | 1 | 40 | Researched databases for training. Found one, attempted to trim dead links. Timeframe is on the scale of days. Not really feasible. Database is still usable, just program around using dead links
29 | John Newman | 2025-02-14 | 1 | 37 | Researched how to train models, spent time prompt engineering, banged my head against a wall, discussed and thought about how model will work and train
30 | Kai Achen | 2025-02-15 | 0 | 20 | tinkered with torch cuda sentence generator prompt using some verbiage from the section508.gov site on what makes appropriate alt-text
31 | Kai Achen | 2025-02-15 | 0 | 20 | created flow chart artifact for what type of alt-text should be generated based on image attributes and website context
32 | Landon Pyko | 2025-02-15 | 0 | 30 | Did some comments
33 | Aiden Patel | 2025-02-16 | 1 | 10 | Added URL image functionality and created 'main' facing method for captioner to connect with scraper in the future
34 | Aiden Patel | 2025-02-16 | 0 | 20 | create worklog
35 | Aiden Patel | 2025-02-16 | 0 | 5 | cleaned up sprint 2 artifacts and submitted it as well as the requirements stack
36 | Aiden Patel | 2025-02-21 | 0 | 5 | fork sprint 1 repo for second sprint and invited the team for collaboration
37 | Aiden Patel | 2025-02-21 | 1 | 10 | Created web scraper and connected it to the captioner in the main_captioner.py file. Ran the test on the lied center site so the output can be seen at lied_center.csv
38 | Aiden Patel | 2025-02-21 | 0 | 23 | create quick script to convert csv output to pdf to show caption next to image
39 | Aiden Patel | 2025-02-21 | 0 | 8 | add pdf creator to test script
40 | Kai Achen | 2025-02-24 | 0 | 20 | learn Aiden's new changes and write some basic information in the README on how to use the project in its current state
41 | Kai Achen | 2025-02-24 | 0 | 30 | fix some import statements and attempted to make web scraper also access images in "revolution slider" (lied specific wordpress plugin) but not working correctly yet
42 | Kai Achen | 2025-02-24 | 0 | 5 | added timer to main_captioner.py
43 | Andrew McFerrin | 2025-02-24 | 0 | 15 | reviewed sprint requirements and understood the scraper code
44 | Landon Pyko | 2025-02-24 | 1 | 0 | tried tinkering with some model generation inputs but didn't make much progress, will look at it again tomorrow
45 | Aiden Patel | 2025-02-24 | 0 | 20 | pushed potentially broken code because I wanted to have it saved in case of a crash. Created test function to test multiple sites so I'm going to run that now to get timings
46 | Aiden Patel | 2025-02-24 | 0 | 20 | thought something was broken with the code so i was crashing out but realized i forgot the 'u' at the end of 'edu' in a url and that's why it was breaking
47 | Aiden Patel | 2025-02-24 | 0 | 30 | added bypass for images that have failures processing or process nothing
48 | Aiden Patel | 2025-02-24 | 0 | 5 | added another thing to handle poor response code from loading an image
49 | Aiden Patel | 2025-02-24 | 0 | 10 | handle poor response code from loading image in PDF creator
50 | Aiden Patel | 2025-02-24 | 0 | 3 | more try except blocks added to catch errors in image loading
51 | Andrew McFerrin | 2025-02-24 | 2 | 0 | Worked on new branch "front_end" to reorganize structure of project to facilitate flask. Created basic flask website with initial necessary elements. Reran main_captioner to ensure it still works with restructured project
52 | Aiden Patel | 2025-02-25 | 0 | 10 | added another dead link check and reviewed test results
53 | Aiden Patel | 2025-02-25 | 0 | 36 | Ran tests and put in some starter code for multiprocessing that is currently blocked from running
54 | Aiden Patel | 2025-02-25 | 1 | 15 | update multiprocessing to be functional without ruining single process option. Ran test on lied center and found 210 second decrease in run time when using 4 processes over 1
55 | Aiden Patel | 2025-02-25 | 0 | 10 | update worklog
56 | Aiden Patel | 2025-02-25 | 1 | 30 | organize files and change code so that dependencies still work and input and output files are handled correctly
57 | Kai Achen | 2025-02-25 | 1 | 0 | restructuring to prepare for Flask implementation and added some functionality for users to mark types of images
58 | Aiden Patel | 2025-02-25 | 1 | 0 | rebase front_end branch to updated file structure. Talk with Kai about file structure so moved new file structure over to main branch. Need to rebase front_end to updated file structure
59 | Aiden Patel | 2025-02-25 | 0 | 10 | pull up flags and front_end_rebase branches to newest version of main with the updated file structure
60 | Aiden Patel | 2025-02-25 | 0 | 15 | fixed path issue and created multiprocess test function to get optimal number of processes
61 | Aiden Patel | 2025-02-26 | 0 | 20 | fix multiprocess test to run on lied center with 1-16 processes
62 | Aiden Patel | 2025-02-26 | 0 | 5 | ran pool tests, everything failed. Pushing results anyway to show how many got through before crashing
63 | Landon Pyko | 2025-02-27 | 1 | 15 | spent forever on dependencies. the flask is acting weird, not sure if it is on just my device or not. started outputting what the errors are. someone else can try to fix that. it might be a me problem but i have no idea
64 | Landon Pyko | 2025-02-27 | 0 | 10 | I got it to not crash on my laptop so that's good
65 | John Newman | 2025-02-28 | 1 | 27 | Spent time researching ways to detect and load desired images
66 | Landon Pyko | 2025-03-01 | 1 | 30 | Flask runs scaper and model when url is input. Once data is finished being process it renders a success page. Someone else could do putting the images with the captions on the flask website for output. for now they just print in the terminal
67 | Aiden Patel | 2025-03-01 | 1 | 30 | generalized the pythonn executable used in index.py so it shouldn't have to be changed between systems. Added output page that loads all images and their alt text after processing is done
68 | Kai Achen | 2025-03-03 | 0 | 20 | updated requirements stack and assigned a few tasks
69 | Aiden Patel | 2025-03-04 | 0 | 10 | update worklog
70 | Andrew McFerrin | 2025-03-04 | 1 | 55 | Reviewed previous video, created script document, wrote/planned out part of script, and made mascot image
71 | Andrew McFerrin | 2025-03-04 | 3 | 10 | Resolved issues with setting up my environment, created intro to video
72 | Andrew McFerrin | 2025-03-06 | 0 | 30 | Wrote/planned out script for website demo on video
73 | Landon Pyko | 2025-03-06 | 0 | 30 | Wrote some stuff for the script and looked more into how to refine our alt text. doing the cosine similarity stuff could be more difficult than we think
74 | Kai Achen | 2025-03-06 | 0 | 30 | Added some words to the script about refined front end and authorization
75 | Andrew McFerrin | 2025-03-06 | 4 | 0 | continued work on the video
76 | Landon Pyko | 2025-03-07 | 0 | 20 | did some stuff
77 | Andrew McFerrin | 2025-03-07 | 3 | 30 | more editing
78 | Kai Achen | 2025-03-07 | 2 | 0 | added to script and created documentation on data types used in each function of the project
79 | John Newman | 2025-03-07 | 1 | 45 | added to script
80 | Kai Achen | 2025-03-08 | 2 | 0 | finalized script and helped find and create some assets for video
81 | Andrew McFerrin | 2025-03-08 | 3 | 0 | more video wow
82 | Andrew McFerrin | 2025-03-08 | 0 | 15 | lil bit o video
83 | Andrew McFerrin | 2025-03-08 | 3 | 0 | finished video(?)
84 | Kai Achen | 2025-03-09 | 0 | 15 | helped make a few more assets for video
85 | Andrew McFerrin | 2025-03-09 | 0 | 15 | Made final adjustments
86 | John Newman | 2025-03-10 | 1 | 0 | made new branch for training the model. made dummy code for when we actually have datasets.
87 | Aiden Patel | 2025-03-11 | 0 | 5 | create pull request for flags branch and merged it over with main
88 | Landon Pyko | 2025-03-12 | 1 | 0 | Made a new branch, reinstalled dependencies on my machine and changed a few lines but now it's not finding my csv??
89 | Landon Pyko | 2025-03-13 | 0 | 35 | It runs but now the output is dog water
90 | Aiden Patel | 2025-03-13 | 0 | 30 | update requirements stack and create artifacts
91 | Aiden Patel | 2025-03-13 | 0 | 10 | update worklog
92 | Aiden Patel | 2025-03-13 | 1 | 0 | Separated scrape and process functions and added function to remove images from CSV. Hitting issues with testing that is causing it to fail to write to CSV
93 | John Newman | 2025-03-14 | 0 | 29 | More work on training file, changed prompt a bit. No real results
94 | Aiden Patel | 2025-03-25 | 0 | 5 | add pycache to gitignore
95 | Aiden Patel | 2025-03-25 | 0 | 30 | finished separating backend functions to allow for exclusions
96 | Aiden Patel | 2025-03-25 | 0 | 45 | created database and started to integrate it into captioning process
97 | John Newman | 2025-03-25 | 0 | 20 | Added support to store training data from captioning process
98 | Andrew McFerrin | 2025-03-25 | 3 | 20 | Created front end for manual image tagging
99 | Andrew McFerrin | 2025-03-26 | 0 | 50 | tried to figure out how to send image link csv to front end
100 | Aiden Patel | 2025-03-26 | 0 | 5 | figure out how to amend commit to remove leaked API key
101 | Landon Pyko | 2025-03-26 | 3 | 0 | Changed model from FLAN-T5 to gemini, seems very promising with about the same runtime. Accidentally leaked the API key (lol) so we tried to fix that. Merged and the old key.txt came back up but it's an old key so it can't be used. Aiden is going to just manually delete the old key.txt file. They can see it in our history but it's dead now anyways so it doesn't matter
102 | Aiden Patel | 2025-03-27 | 1 | 10 | Hashing into database and fetching them later is now working. Need to make it where timestamps update on each retrieval and DB purges when it hits a certain size but I'll get to it later
103 | Aiden Patel | 2025-03-27 | 0 | 23 | Changed where timestamp updates for each access and DB will purge the oldest timestamp when more than 500 entries are present. Also added flag in create_caption that can be changed when forcing the model to not check the DB and compute instead
104 | Aiden Patel | 2025-03-27 | 1 | 10 | Updated index.py on main branch and pulled up image_exclusions and cache_computations branches with new changes. Moved functionality in image_exclusions branch into new main.py function but will need to be split later. Ran site tests on cache branch to update database. Database hashing is probably ready to merge into main soon but will likely cause a few merge conflicts on other branches
105 | Landon Pyko | 2025-03-27 | 2 | 0 | Entirely removed the text processing step from the pipeline, and have gemini working with the output. I also tried seeing how gemini's image captioning would be (as opposed to blip's) and it's lowkey better. Anyways, I just made a different captioning function that calls gemini instead of blip so everything is still in there and we can evaluate output later
106 | Landon Pyko | 2025-03-28 | 0 | 20 | Looking into chrome extensions
107 | Aiden Patel | 2025-03-28 | 1 | 0 | Talked to Landon about Gemini and merged into main. Pulled up other branches to have new changes. Ran tests on cache branch to begin updating database with new Gemini responses
108 | Aiden Patel | 2025-03-28 | 4 | 0 | Connected selection function with front end to allow for user tagging
109 | Kai Achen | 2025-03-29 | 0 | 10 | update requirements stack
110 | Aiden Patel | 2025-03-29 | 0 | 30 | cleaned up image_exclusions branch and merged into main
111 | Aiden Patel | 2025-03-29 | 0 | 20 | update cache branch with main and then merged it into main
112 | Andrew McFerrin | 2025-03-30 | 0 | 30 | Created sprint 5 artifacts document
113 | Andrew McFerrin | 2025-03-30 | 0 | 30 | Watched a few videos on how to set up tailwind in a project and basic use
114 | John Newman | 2025-03-30 | 2 | 0 | Updated files for training. create_caption.py: changed gemini generate to call with training args gemini.py: added arguments for training, added code to collect data if training train_flan.py: Changed code to just be for cleaning up datasets and providing good data to them. Added a tkinter image and entry for data collection.
115 | John Newman | 2025-03-30 | 0 | 11 | Added some things to sprint 5 artifacts.
116 | Aiden Patel | 2025-03-30 | 0 | 17 | Finished requirements stack and artifacts for sprint 5 and submitted
117 | Aiden Patel | 2025-03-30 | 0 | 10 | update worklog
118 | Kai Achen | 2025-04-01 | 0 | 30 | added home navigation button to displayed_images.html and a loading circle to help communicate that the site is working in the background
119 | Aiden Patel | 2025-04-01 | 1 | 0 | Added default tag of "don't include" for images with that don't load. Mainly just works for links that aren't pulled properly so they shouldn't be displayed at all ideally. Also added an exception catch when generating from Gemini if a ResourceExhausted error occurs. Manually sleeps the process and attempts to regenerate rather than crashing the program now
120 | Aiden Patel | 2025-04-01 | 0 | 20 | Added URL validation and sanitation
121 | Andrew McFerrin | 2025-04-02 | 1 | 45 | Fixed up some ui issues with tagging and started work on integrating given website into tagging page
122 | Landon Pyko | 2025-04-03 | 1 | 0 | Trying to get js to just connect to our local host so we can communicate with the server for extension purposes. Need to install a dependency to do cross-origin resource sharing. I have it installed but for some reason it's not detecting it. Will look at it tomorrow probably. done for tonight
123 | Landon Pyko | 2025-04-04 | 0 | 10 | Sample js+html is able to connect to flask server
124 | Andrew McFerrin | 2025-04-06 | 3 | 0 | Fixed some front end displaying issues, added website view when tagging images, created an add image button for including images in tagging that werent found by scraper
125 | Kai Achen | 2025-04-06 | 2 | 0 | added Oauth login with Google (still need to make it work well but it's connected) but can't commit changes because "leaking keys" (using environment variables to store keys, I guess it doesn't like that?)
126 | Kai Achen | 2025-04-07 | 0 | 20 | fixed commit history to no longer contain plaintext keys
127 | Kai Achen | 2025-04-07 | 2 | 0 | tried deploying on google app engine, waiting on results to load
128 | Landon Pyko | 2025-04-07 | 0 | 30 | Extension is able to actively communicate with our server. Now just need to call the scraping lowkey
129 | John Newman | 2025-04-07 | 1 | 19 | made datasets save properly, starting trying to make google do the training for me
130 | Kai Achen | 2025-04-07 | 0 | 30 | made a few dependencies import individual methods instead of the whole library
131 | Aiden Patel | 2025-04-07 | 1 | 30 | Began to refactor the codebase by renaming files and functions as well as removing unused code and combining redundant code. Still a work in progress so it is sitting on the clean_codebase branch
132 | Aiden Patel | 2025-04-08 | 1 | 30 | Created another class to combine multiple files and removed more unused files. Backend is largely reformatted now and safe to merge into main. The test script doesn't work and will need to be changed if used
133 | Aiden Patel | 2025-04-08 | 0 | 30 | Reduce imports to what is needed and created pull request for clean_codebase branch. Waiting for code review from Landon and Kai before merging into main
134 | Aiden Patel | 2025-04-08 | 1 | 0 | added filtering to remove inputs into Gemini when data does not exist so that output is more consistent. Added handling of decorative images by returning empty tag and fixed hashing to correctly include tags so that cache is accurate.
135 | Aiden Patel | 2025-04-08 | 0 | 20 | added href to the scraped data tuples for use in link annotations later
136 | Andrew McFerrin | 2025-04-09 | 2 | 0 | added front end url cleaning and started working on trying to get around SOP
137 | Aiden Patel | 2025-04-09 | 1 | 30 | added support for link annotation to describe destination site. Cleaned up the rest of the code on the branch and merged it into main
138 | John Newman | 2025-04-10 | 2 | 16 | rebased and got on the right repo finally, Move dataset creation support to DataProcessor class data_proccesor.py: added imports for functions needed for saving training dataset, added argument to determine whether data should be used in training, added branch for training in informative alt text and link alt text generation, added function _save_to_dataset to save url, prompt to dataset More stuff about training datasets db,.csv, and .jsonl are datafiles. train_flan renamed to training training.py: Convert loose methods to a class, add exception checking for loading images and json data, add more stuff to tkinter window to make the annotation easier
139 | Aiden Patel | 2025-04-10 | 1 | 20 | started migrating the cache to the database and created the database for user generation storage. Still having issues with API key for supabase so I'll finish up later
140 | Aiden Patel | 2025-04-10 | 2 | 0 | created new tables to handle future user retrieval and stored the schema visualization in documents. Fixed bugs so that Supabase caching now works but is for some reason limited to only working in the Python Debugger on VSC. Spent a bunch of time debugging and can’t seem to find a reason so I’ll need to look into it further later
141 | Landon Pyko | 2025-04-10 | 1 | 0 | Able to send the current window url over to our server and it scrapes data, just need to properly redirect and handle that stuff. Will fix it later
142 | Aiden Patel | 2025-04-10 | 0 | 40 | in my sisyphus era trying to defeat the debugger gate keeping my correct execution
143 | Aiden Patel | 2025-04-10 | 0 | 30 | more sisyphus
144 | John Newman | 2025-04-10 | 0 | 10 | Running tests for aiden. Checking if supabase works on other systems
145 | John Newman | 2025-04-11 | 2 | 5 | Added support to create fine tuned models data_processor.py: added import of the trainer, removed uneeded imports, changed training flag behavior to make a trainer if training is true, else none, changed prompt collection to use Trainer class instead of having dedicated function, remove save_to_dataset as Trainer handles that operation jsonl files: created during testing training.py: changed add_to_dataset args to remove datasetfilename and add image type, filename is now made from modelname and image type, create a functional create_gemini_model function which takes in a dataset filename, loads it, converts to google TuningDataset, creates a tuning job on the client with that dataset and print the job, create check_tuning_job_status to check how a job is going, currently only checks a hardcoded job, but could not do that with 1 line change. Default behavior of training.py now lists models and checks the status of a training job.
146 | Landon Pyko | 2025-04-12 | 1 | 30 | Extension is done.
147 | John Newman | 2025-04-12 | 1 | 13 | fine tune and use a model support data_processor.py: hardcoded the usage of a tuned model. needs to be refined and updated to the new api as well site_processor.py: I scared the module loader so now genai refers to its own thing so chagnge alias to genal training.py: updated create gemini model to actually use the data instead of the strings"text_input", "output" repeatedly. Added support in check_tuing_job_status to check any job. changed default behavior to do a lot of things for testing.
148 | Andrew McFerrin | 2025-04-12 | 0 | 30 | started creating front end for history of scraped websites
149 | Kai Achen | 2025-04-13 | 0 | 30 | updated requirements and generated artifacts for final sprint
150 | Andrew McFerrin | 2025-04-13 | 0 | 45 | worked more on making history page
151 | John Newman | 2025-04-13 | 0 | 50 | Added full support for using tuned model/s data_processor.py: added arg to use tuned model to constructor, added attribute to determine usage of tuned model/s, moved prompts to prompt var instead of copying for a third time,added support to use the 'icran' tuned model Deleted unused or unusable jsonl files training.py: specified the imports to cut down on import files, added comments, added self to complte_dataset, Changed default behavior to be listing all tuned models. Created pull request for the branch as the goal seems to be accomplished
152 | Aiden Patel | 2025-04-13 | 0 | 5 | pull request review for training branch. Left one comment just to make sure there aren’t any issues
153 | John Newman | 2025-04-13 | 0 | 5 | fix the commented issue (using improper model for link alt text generation)
154 | Aiden Patel | 2025-04-13 | 0 | 2 | merged training branch into main and deleted the branch
155 | Andrew McFerrin | 2025-04-13 | 0 | 20 | finished up barebones history page
156 | John Newman | 2025-04-14 | 0 | 33 | Testing aidens phantom api Key error. moved to database_support branch, ran flask app in normal mode, got wrong API key error, confirmed i had the correct key, tried again, same error. Issue persisted in debug mode, then I close and reopened my terminal in vscode and it worked
157 | John Newman | 2025-04-14 | 0 | 3 | Moved to new fork and updated requirements doc
158 | Aiden Patel | 2025-04-15 | 1 | 15 | solved database connection issue and started UserInfo class
159 | John Newman | 2025-04-15 | 0 | 53 | Updated files to use new genai api over old one data_processor.py: Changed to use model name and a client to generate content instead of a model site_processor.py: removed generativeai import, added genai import, changed attributes to get client and model name instead of model class. Also did testing to confirm project works as before. It performs identically to before on ku.edu and lied.ku.edu Optimized to generate client once data_processor.py: changed import from model name to client, renamed dummy_client to gemini_client, hardcoded model name to be gemnini 1.5 flash, updated rest of code respectively. site_processor.py: removed unused commented code, changed call to dataprocessor to use client instead of name Update data_processor.py used tuned model by default Merge branch with main: Update the project to use the updated and not deprecated version of the google genai api.
160 | Aiden Patel | 2025-04-15 | 0 | 40 | created UserInfo class but currently untested
161 | Aiden Patel | 2025-04-15 | 0 | 40 | start looking on how to remove subprocess calls
162 | Aiden Patel | 2025-04-15 | 2 | 0 | remove subprocess calls in flask and CSV read/writes as well as old CSV output data. Created new main.py to connect to backend objects and allow flask to make calls. Created pull request and awaiting reviews
163 | Kai Achen | 2025-04-15 | 0 | 30 | update oauth branch to work with new main architecture
164 | Aiden Patel | 2025-04-15 | 0 | 5 | pulled up database branch to main
165 | Aiden Patel | 2025-04-17 | 2 | 0 | restructured database system to match the conversation with Kai yesterday and finished integrating support. Caching should now be seamless and tables for users and past generations are present. Database backend support for regenerating images and adding images to generations is now added and waiting to be connected to OAuth and front end updates. Added try-except blocks to catch Supabase errors to avoid system crashing if environment bugs are still present
166 | John Newman | 2025-04-17 | 0 | 10 | code review for aiden
167 | Aiden Patel | 2025-04-17 | 0 | 5 | addressed John's and removed usernames
168 | Aiden Patel | 2025-04-17 | 0 | 5 | update database schema and created to-do list
169 | Aiden Patel | 2025-04-17 | 0 | 10 | update worklog
170 | Aiden Patel | 2025-04-17 | 0 | 45 | started trying to get the site hosted on Render for testing and got rid of a few bugs found by Landon
171 | Aiden Patel | 2025-04-17 | 0 | 45 | solved cookie issue by moving session data to be stored in Supabase and handled server side. Merged that into main and then merged Supabase database changes into main too
172 | Aiden Patel | 2025-04-17 | 0 | 7 | reviewed the extension pull request and left a few minor comments to handle before merging
173 | Aiden Patel | 2025-04-17 | 0 | 15 | change imports so that they can be accessed with gunicorn on Render
174 | Aiden Patel | 2025-04-18 | 0 | 5 | pulled up Andrew's front end branch and tested, appears to be working as intended
175 | Kai Achen | 2025-04-18 | 2 | 0 | fixed oauth branch issues and finished implementing button correctly. waiting on pull request now
176 | Andrew McFerrin | 2025-04-18 | 3 | 0 | added lil buttons on front end to the gallery to allow for alt-text regeneration, added sidebar to pull out/collapse iframe, added file drop box for users to drag images in to add
177 | Landon Pyko | 2025-04-18 | 1 | 0 | Ran aidens stuff and found printing issues
178 | Aiden Patel | 2025-04-18 | 0 | 35 | reviewed Kai's pull request and made some changes to match structure. Also fixed a bug with saving generation data. Merged OAuth into main now
179 | Aiden Patel | 2025-04-18 | 2 | 0 | started to create more endpoints to allow for proper functionality with new front end features on front end branch. Regenerate image button and history page are now accurate
180 | Kai Achen | 2025-04-18 | 2 | 0 | added support for no images found when scraping as well as another loading bar after the start scraping button has been pressed
181 | Kai Achen | 2025-04-18 | 0 | 20 | tracked down likely reason for manually adding images not running through the model. added comment in push to oauth branch
182 | Aiden Patel | 2025-04-19 | 0 | 30 | A few more changes to loading previous results page. Still doesn't work though.
183 | Aiden Patel | 2025-04-20 | 1 | 40 | Finished adding support for the add images feature. Front end new features are now all connected as far as I can tell so I'm making a pull request.
184 | John Newman | 2025-04-20 | 1 | 29 | Code review and test for aiden pull gone wrong. Issues with generating alt text for large images, performance issues once big images are associated with an account (immense slowdowns), potentially(not fully tested(got bored)) locked out of site if logged into site through browser(ie autologin) but incognito and then logging in works. Otherwise it works great, minus the 2 other things noted in pull request
185 | Aiden Patel | 2025-04-20 | 1 | 30 | Addressed comments from John and added resizing of images and database restructure for storing uploaded images
186 | Aiden Patel | 2025-04-20 | 0 | 10 | did some more intensive testing by uploading 16k images that are 30 MB and the site appears to be handling it
187 | John Newman | 2025-04-20 | 0 | 26 | code review and testing for aiden. Still blocked from autologging in, it causes a timeout. But incognito to login to running works.
188 | Kai Achen | 2025-04-20 | 0 | 10 | code review for Aiden
189 | Kai Achen | 2025-04-20 | 2 | 0 | added features to small_changes branch:
190 | Aiden Patel | 2025-04-20 | 0 | 2 | merge front end into main and close pull request
191 | Aiden Patel | 2025-04-22 | 2 | 0 | Add session variables clearing. Fix changes on extension branch and merged into main. Start working on more render changes to deploy online
192 | Aiden Patel | 2025-04-22 | 1 | 40 | Successfully got everything up on Render but it seems that the free plan will not have enough resources to run our server. Added email alert feature on a new branch
193 | Kai Achen | 2025-04-22 | 0 | 20 | worked with Aiden to figure out branch weirdness and create pull request for small changes branch
194 | Aiden Patel | 2025-04-22 | 0 | 20 | reviewed Kai’s pull request and left comments
195 | Landon Pyko | 2025-04-22 | 0 | 20 | changed the things on the extension branch that aiden told me to and then merged
196 | Kai Achen | 2025-04-22 | 0 | 20 | made an entirely new branch based off current main in order to manually add the correct changes from small_changes branch and now it seems to work correctly, so made new pull request
197 | Aiden Patel | 2025-04-22 | 0 | 10 | re-reviewed Kai's pull request and tested the new features. Accepted the changes and merged into main
198 | Aiden Patel | 2025-04-23 | 0 | 20 | added logout button to email branch and created a pull request
199 | John Newman | 2025-04-23 | 1 | 0 | code review for aiden. QA, malicious testing. Revealed that we need redirects or something
200 | Aiden Patel | 2025-04-23 | 0 | 20 | Tested John's found issues and was able to recreate. Added early exits for invalid pages and blocked caching at some pages for hiding user data so those breaking cases seem to be handled now
| Andrew McFerrin | 2025-04-23 | 2 | 0 | Talked with landon about website layout, created a new branch for website visuals, and added basic topbar to each page with some other visual changes
| John Newman | 2025-04-23 | 2 | 50 | Added input and output types to all python functions Aiming to make code more readable and facilitate ease of use for other devs
| Aiden Patel | 2025-04-23 | 0 | 10 | added URL error catching to prevent crashes for invalid URLs being entered on the home page
| Aiden Patel | 2025-04-23 | 0 | 40 | added support for downloading generations as a CSV, JSON, or HTML file to better cater to the "for developers" vision
| Aiden Patel | 2025-04-23 | 0 | 20 | Merged email branch pull request. Pulled up new download options branch. Changed name of added images when downloading to not return base64. Created pull request
| Landon Pyko | 2025-04-23 | 0 | 30 | talked with andrew about website layout. grabbed a template, and started modifying it to fit our purposes
| Aiden Patel | 2025-04-24 | 1 | 45 | spent time trying to fix the web scraper for the KU site. Turns out we are actually scraping the image URLs properly but KU must be loading an image from the backend because loading that URL anywhere besides on the KU site just returns the single pixel
| Aiden Patel | 2025-04-24 | 0 | 30 | added filtering to remove single pixel images and solid color images
| Andrew McFerrin | 2025-04-24 | 0 | 50 | dripped out website a bit more and added login/logout button logic
| Aiden Patel | 2025-04-24 | 0 | 15 | patched the regeneration bug that was loading the wrong image when an image was not included
| John Newman | 2025-04-24 | 2 | 0 | Delete unused code Delete code that isn't being used Arbitrary training things Aiden got me distracted by complaining about the logo issue. Added more types, removed code data_processor.py: removed unused code user_info.py: added typing to _get_email and email_user web_scraper.py: added typing to _filter_images and in scrape_site index.py: added typing to vars inside of fucntions. Changed text in prints for dowloads to accurately represent actual issue.
| Andrew McFerrin | 2025-04-24 | 1 | 10 | added consistant styling to generated alt-text results, attempted to work on on more personalized page titles
| Landon Pyko | 2025-04-24 | 0 | 45 | Made the form and start scraping button look better. Also fixed the final results page so that text does not overflow into the next image card. As of now if there is too much text there is a scroll bar, but that can be changed. Planning on adding the alt-text admiral to the bottom of the first page and will look into that ship thing. Also going to create about page
| John Newman | 2025-04-24 | 1 | 3 | Updating documentation for future users. Anyone else please add documentation when convenient. Added input and output types to all python functions Update README.md New readme which more accurately reflects the project Requested review from @everyone as If I fucked up the typing its probably an issue for everyone
| Aiden Patel | 2025-04-24 | 0 | 30 | Tested and reviewed John's documentation pull request
| Aiden Patel | 2025-04-25 | 0 | 5 | re-reviewed John's pull request then approved and merged into main
| Aiden Patel | 2025-04-25 | 0 | 30 | tried to find a solution to showing a website side by side on our site. Proxy wasn't working but I did find an error in how the URL was being received by the HTML so I fixed that
| John Newman | 2025-04-25 | 1 | 27 | Updating training to be run individually temp_scripting.py: Created a python script to create a list of all the websites located in the Supsbase site generation table training.py: Add attributes to faciiitate training. Add collect_from_sites which makes unprocessed datasets from a list of websites. add generate_image_caption for use in the prompt. Add generate_image_objects for use in the prompt. Add prompt_generator to create the prompt text. Ran the file to collect website data in website.txt index.py: added one type i missed before. add websites.txt to git ignore on the premise of security
| Kai Achen | 2025-04-25 | 3 | 0 | tried to deploy as .exe file but ran into lots of errors with imported libraries and stuff that we didnt write. quite frustrating, don't think it'll work.
| Kai Achen | 2025-04-26 | 0 | 30 | added user alert for invalid URL entry
| Landon Pyko | 2025-04-26 | 1 | 15 | CSS stuff. Not sure how feasible adding the ship will be. Need to write info for about the team and at the bottom of the front page
| Landon Pyko | 2025-04-27 | 0 | 30 | More stuff
| Landon Pyko | 2025-04-27 | 0 | 30 | More
| Kai Achen | 2025-04-27 | 2 | 30 | working on front end to make it wcag compliant and look a little nicer
| Aiden Patel | 2025-04-27 | 2 | 30 | worked on team call and added ship loader. Merged dripped out branch into main
| Kai Achen | 2025-04-27 | 0 | 30 | fixed a few weird things like history page spacing
| John Newman | 2025-04-27 | 3 | 15 | Updated about us images to have pirate themes
| Kai Achen | 2025-04-27 | 1 | 0 | more small assorted changes
| Andrew McFerrin | 2025-04-27 | 1 | 0 | helped a bit with ship animation
| Aiden Patel | 2025-04-27 | 2 | 30 | more front end refinements
| Kai Achen | 2025-04-27 | 0 | 20 | updated README
| Aiden Patel | 2025-04-27 | 1 | 30 | created demo video, uploaded it to youtube and embedded on README. Updated final worklog entries